## Slide 1
TerrADat
Design Database
Study Area
Design Strata
Design Weights
Point Fate
Benchmark Strata
Reporting Units
Project Design Workbook
Objectives
Indicators
Benchmarks
Weight Calculation
Summarize Data
Calculate Indicator Estimates
Cat.analysis Output
Create Report, Charts, Maps
Data Explorer Workbook
Add Indicators, Benchmarks for Objectives by Strata
Data Frame with Weights
Plot IDs
TerrADat Indicators
Weights column
Reporting Unit Column
Benchmark Stratum column
X,Y Coordinates
Remote Sensing Products
Grass/Shrub
Landfire EVT
…
Output Report
AIM Analysis Sprint Workflow
2
3
4
5
1

## Slide 2
Input
Scripted Process
Manual Process
Temporary Output
Preserved Output
Excel Workbook
Word Document
Tabular Data
Spatial Data
R Script
R Markdown
Legend
1
2
3
4
5
Complete the sample design geodatabases for the projects. Decide how to handle point fate information in standardized way.
Create scripts to automatically populate the Data Explorer Workbook for projects. Or manually create the Data Explorer Workbooks for the Sprint projects and add the objectives in.
Scripting for calculation of point weights.
Scripting of analysis for calculating area-based estimates.
Scripting the R Markdown document for generating the output report/graphs/tables/maps from the analysis results and other inputs.
Nelson, Nichole, Jennifer, Jason
Jason, Sarah L., Emily
Sarah M., Steve G., Nichole
Nelson, Sarah B.
Jason, Emily, …
Parallel Tasks
Who?
Much of the development work for the Sprint can happen in parallel if we can agree upon consistent formatting for several key pieces. These key convergence points are listed as the outputs (green boxes) in the workflow diagram.